## Slide 1
IEEE Aerospace Electronic Systems Society and Council Review Committee
(SCRC)
Walt Downing, P.E.
2025 AESS Officer Strategic Planning Meeting
28 February – March 1, 2025
Big Sky, Montana, USA

## Slide 2: Outline
What is SCRC?
SCRC Report – Writing Assignments
Next Steps
Timeline

## Slide 3: What is SCRC?
Society and Council Review Committee (SCRC) is a standing committee of the TAB Management Committee (TMC)
SCRC reviews each society or council once every five years
Intended to help societies and councils follow effective practices
AESS last review was in 2020
Process and Schedule:
  Friday, June 20, 2025 - AESS submits a written report to SCRC
  Thursday, July 10, 2025 (Time TBD) - AESS participates in a 105-minute virtual meeting with SCRC to answer questions on each section of the written report
  ~ 1 month later - SCRC assembles comments and send findings to AESS
  ~ 1 month later - AESS responds to comments and findings
  November meeting series - SCRC submits report to TAB TMC and TAB

## Slide 4: SCRC Report – Writing Assignments
* Volunteers are responsible for section content.

## Slide 5: Next Steps
Access SCRC Review Google Drive Folder
Read 2020 SCRC Review Final Report
  Focus on assigned section, but skim entire report for context/overlap
Download copy of 2025_SCRC_AESS_Review_ver_1
Review assigned section
  Identify changes from 2020 report
  Identify and collect information to prepare 2025 report
Prepare initial draft for assigned section
  Okay to cut and paste from 2020 report when relevant
  Ensure consistency of information with governing documents & website
  Save draft copy in Initial Drafts Folder
    File name “Section_X_Author_draft_v1”

## Slide 6: Timeline
Friday, February 28, 2025 – Kickoff
Monday, March 31, 2025 – zoom meeting to review status, share initial inputs, and identify issues
Monday, April 21, 2025 – Section writeups due
Saturday, May 10, 2025 – AESS BoG meeting (review report)
Friday, June 20, 2025 – Report submission deadline
Thursday, July 10, 2025 – zoom meeting with SCRC
* Conference Catalysts’ role in preparing the SCRC report is solely to provide support in finding information or making connections with IEEE staff to obtain information. Amanda can assist with information requests up until May 1, 2025 (pending any changes to her delivery date).

## Slide 7: Questions and Discussion
Questions regarding SCRC Report content should be directed to:
  Walt Downing, SCRC Review AdHoc Committee Chair
    w.downing@ieee.org
    Cell: (210) 573-3635 – Also reachable by WhatsApp, FaceTime, Messenger, etc.